O!Sapiens

18-Month Pre-Seed Roadmap  ·  Sleep recovery, stress resilience, biomarker-informed coaching

## Status overview

Stage: pre-seed validation. Solo founder, Cyprus entity, Spain-based operations. Audience: ~1,700 newsletter subscribers, ~10 paid customers, small community. Wedge: sleep recovery + stress resilience, with biomarker-informed coaching staged as a premium layer in months 13–18.

Funding plan: €500k pre-seed (SAFE / convertible), 12–18 months runway. The round funds MVP build, wearable integrations, Spanish lab partnerships, compliance baseline, and the validation work needed to earn a €1.5–3M seed.

Format: timeline / Gantt across 6 quarters. Each row is an initiative; cells are shaded for the quarters it spans, color-coded by theme.

## Timeline — 6 quarters × 18 months

Color legend:

| Product / Build | Pilots / Growth | Fundraising | Team / Hiring | Compliance |
| --- | --- | --- | --- | --- |

| Initiative | Owner | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Month span | M 1–3 | M 4–6 | M 7–9 | M 10–12 | M 13–15 | M 16–18 |
| Close €500k pre-seed (SAFE / convertible) | Founder |  |  |  |  |  |  |
| Cyprus + Spain legal, IP, GDPR foundation | Founder + counsel |  |  |  |  |  |  |
| Customer discovery — 20–30 interviews | Founder |  |  |  |  |  |  |
| Seed deck + investor pipeline build | Founder |  |  |  |  |  |  |
| Seed raise (€1.5–3M target) | Founder |  |  |  |  |  |  |
| Hire developer (full-stack mobile) | Founder |  |  |  |  |  |  |
| Onboard medical advisor (fractional) | Founder |  |  |  |  |  |  |
| Hire BD lead — lab partnerships | Founder |  |  |  |  |  |  |
| Hire marketing manager | Founder |  |  |  |  |  |  |
| MVP scope + pricing hypothesis frozen | Founder + developer |  |  |  |  |  |  |
| Build MVP — check-ins, 10-pillar, protocols | Developer |  |  |  |  |  |  |
| Apple Watch integration (sleep, HRV) | Developer |  |  |  |  |  |  |
| Oura + sleep app integration | Developer |  |  |  |  |  |  |
| Coaching prompts + protocol engine v2 | Developer + medical adv. |  |  |  |  |  |  |
| Closed beta — newsletter cohort (50–100) | Marketing + Founder |  |  |  |  |  |  |
| Retention instrumentation — D30/D60/D90 | Developer + Founder |  |  |  |  |  |  |
| Pricing & paywall A/B test | Marketing + Founder |  |  |  |  |  |  |
| Open paid launch (Spain + EU) | Marketing |  |  |  |  |  |  |
| Founder content, workshops, community growth | Founder + Marketing |  |  |  |  |  |  |
| Spanish lab BD — 2–3 partnerships signed | BD lead |  |  |  |  |  |  |
| Biomarker coaching MVP (educational, non-dx) | Developer + medical adv. |  |  |  |  |  |  |
| Premium tier compliance + medical review | Medical adv. + counsel |  |  |  |  |  |  |

# Quarter-by-quarter detail

### Q1 — Months 1–3: Foundation

Funding: Close €500k pre-seed. Recommended structure: SAFE or convertible into Cyprus entity, with future Spanish operating sub clearly flagged for investors.

Team: Hire #1 (full-stack mobile developer). Onboard medical advisor on fractional retainer to anchor the coaching framework and compliance posture.

Discovery: 20–30 structured interviews with current paid customers, course participants, and newsletter subscribers. Goal: validate the sleep-recovery / stress-resilience wedge, willingness to pay, and pricing tier hypothesis.

Product: Freeze MVP scope. Lock pricing hypothesis (e.g., €15 basic / €39 premium / €99+ biomarker-informed). Design system + 10-pillar onboarding flow.

Compliance: GDPR foundation, privacy policy, health-data handling. Confirm legal posture (educational, non-diagnostic) in product copy.

Exit gate: Validated wedge + locked MVP scope + advisor signed. Developer ramped. €500k closed and runway clock running.

### Q2 — Months 4–6: MVP Build & GTM Prep

Product: Build core MVP — daily check-ins, 10-pillar onboarding assessment, protocol library, progress tracking. Apple Watch + Oura research and integration spike.

Team: Hire BD lead to start Spanish lab outreach. Begin marketing manager search.

BD: Start outreach to Spanish labs and biomarker providers. Goal: shortlist 5–10, get into commercial conversations with 2–3.

Compliance: Medical / compliance boundary documented. Privacy review against EU health-data rules. Decision: do we need a Spanish operating subsidiary by EOY.

Exit gate: Closed-alpha-ready MVP. BD pipeline of 5+ labs. 2 of the 4 validation questions de-risked through interviews and prototype testing.

### Q3 — Months 7–9: Closed Beta + Wearable Layer

Product: Apple Watch integration shipped. Oura + sleep app integrations in beta. Retention instrumentation in place (D7 / D30 / D60 KPIs).

GTM: Closed beta to 50–100 newsletter subscribers. Marketing manager hired and running the cohort. Founder content + first Spanish workshop.

Pricing: Pricing & paywall A/B test in motion. Begin measuring true willingness-to-pay vs. course pricing baseline.

Lab: First LOI or pilot agreement with a Spanish lab. Define data + workflow shape for biomarker integration.

Exit gate: First paying subscribers (target 50+). D30 retention benchmark established. One signed lab partnership in motion.

### Q4 — Months 10–12: Open Launch + Subscription Validation

Product: Coaching prompts + protocol engine v2. Polish based on beta retention data. Premium tier feature scoping.

GTM: Open paid launch in Spain + EU. Founder-led content + community ramp. Begin paid acquisition tests on small budgets.

Validation: Hit the four pre-seed questions head-on: acquisition efficiency, paid conversion, repeat engagement, differentiation.

Lab: 2–3 Spanish lab partnerships signed. First customer using bundled lab + app.

Exit gate: 200–300 paid subscribers. D60 retention measurable. Pricing tiers validated. Seed story starts to write itself.

### Q5 — Months 13–15: Biomarker Layer + Seed Prep

Product: Biomarker-informed coaching MVP — educational, non-diagnostic. Blood panel trend tracking surface. Premium tier in market.

Compliance: Medical advisor sign-off on biomarker interpretation copy. Premium tier compliance review.

GTM: Cohort 3+ live. Optimize CAC channels that worked in Q4. Earliest B2B / partnership conversations (insurer, NGO, journalist assoc.).

Seed prep: Build seed deck. Update memo. Confirm Spanish operating subsidiary plan if needed. Begin investor warm-up.

Exit gate: Premium tier live with paying users. Biomarker-informed coaching live for at least one cohort. Seed deck ready.

### Q6 — Months 16–18: Seed Raise + Scale Prep

Funding: Run seed raise (target €1.5–3M). Use traction story: subscribers, retention, lab partnerships, biomarker pilot.

Product: Hardening + scale prep. Backlog grooming for post-seed roadmap (Spain ⇒ EU expansion, deeper biomarker layer).

Team: Hire #5 (likely senior eng or growth). Plan post-seed org chart.

GTM: Continue cohort and content. Begin scaled paid acquisition tests if unit economics allow.

Exit gate: Seed closed. Clear evidence on all four pre-seed validation questions. Defined path to 1k+ paid subscribers and second product tier in market.

# Hiring plan tied to milestones

Capacity assumption: pre-seed, lean. Each hire is sequenced to where it unblocks the next exit gate, not by org-chart aesthetics.

- Q1 — Developer (full-stack mobile). Unblocks MVP build and wearable integrations. Hire as employee or long-term contractor depending on Cyprus/Spain structure.

- Q1 — Medical advisor (fractional). Anchors the coaching framework and the educational-vs-diagnostic compliance boundary. Likely 4–8 hrs/month retainer.

- Q2 — BD lead (lab partnerships). Owns Spanish lab outreach end-to-end. Comp-light, equity-meaningful; first hire facing customers / partners.

- Q3 — Marketing manager. Owns the newsletter → paid funnel, content, workshops, and launch motion. Hire ahead of the closed beta, not after.

- Q5 — Senior eng or growth lead (#5). Funded by seed momentum or bridge. Tees up post-seed scale.

- Ongoing — Advisory board. 2–3 named advisors before the seed deck goes out: ideally one healthspan / clinical name, one consumer subscription operator, one EU regulatory / privacy voice.

# Risks and dependencies

Retention risk. Consumers paying for ongoing coaching is harder than one-off courses. Mitigation: instrument retention from day one; design check-ins, streaks, and protocols to deliver weekly value; benchmark against best-in-class wellness subscriptions.

Wearable / integration. Apple Watch, Oura, and sleep app APIs each carry approval and reliability risk. Mitigation: scope MVP so wearable data enriches but is not required for value; sequence Apple Watch first, Oura second.

Lab operational scale. Lab partnership workflows are fragile and slow. Mitigation: start with 1 lab end-to-end before signing 3. Build minimum workflow tooling rather than a marketplace.

Compliance boundary. The line between educational and diagnostic guidance is enforced and easy to cross. Mitigation: medical advisor reviews biomarker copy; explicit non-diagnostic disclaimers; clinical oversight before any treatment-adjacent feature.

Founder dependency. Solo founder + Cyprus entity is a real signal for investors. Mitigation: medical advisor + early hires + named advisory board before seed.

Differentiation vs. peers. Function Health, InsideTracker, Whoop, Oura, coaching apps all compete on adjacent surface. Mitigation: own the 10-pillar behavior-change layer; lean into Spain + EU GDPR-native positioning; pair biomarker + behavior in one experience.

# Validation milestones (the four pre-seed questions)

These are the four questions the round is designed to answer. The roadmap should be re-cut anytime data on these shifts.

- Can O!Sapiens acquire users efficiently from its existing audience and adjacent communities? — measured in Q3–Q4 via newsletter → paid conversion, workshop attribution, and earliest paid acquisition tests.

- Will users pay for a subscription beyond courses or one-off education? — measured in Q3 closed beta and Q4 open launch, pricing A/B test, paid conversion vs. course baseline.

- Can the product drive repeat engagement through daily check-ins, protocol completion, wearable syncing, and coaching interactions? — measured Q3 onward, D30 / D60 / D90 retention benchmarks.

- Can O!Sapiens create a differentiated position against biomarker and healthspan platforms (Function Health, InsideTracker, Whoop, Oura)? — measured by Q4–Q5 via positioning tests, lab-bundled cohort outcomes, and qualitative customer differentiation interviews.

## Top-line milestones

Month 3 — €500k closed. Developer + medical advisor onboarded. MVP scoped. 20+ discovery interviews complete.

Month 6 — MVP closed-alpha. BD pipeline of 5+ labs. Compliance + privacy baseline live.

Month 9 — 50+ paying subscribers from closed beta. D30 retention number we can defend. First signed lab partnership.

Month 12 — 200–300 paid subscribers. 2–3 lab partnerships live. Pricing tiers validated. Four pre-seed questions answered with data.

Month 15 — Premium / biomarker-informed tier in market. Seed deck and metrics deck ready. Investor warm-up underway.

Month 18 — Seed (€1.5–3M) closed or near close. Clear playbook for Spain ⇒ EU expansion.