# FOUNDER EXECUTION OS

## Vladislav Andreev. July 2026 - June 2027.

### Converts the Master Strategy into daily operation. This document does not create new strategy. It makes the existing one executable.

Document conflicts found and how they were resolved (read this first):

- Your LinkedIn profile currently violates your own brand separation rule. The summary mentions "conscious, harm-reduced use of entheogens" and links entheogen.expert. The Brand Strategy says LinkedIn carries O!Sapiens only. Resolution per hierarchy: Brand Strategy wins over legacy profile copy. Fix in Week 1. This is not cosmetic. Corporate buyers and HR gatekeepers screen you before workshops, and this line costs you deals you never hear about.

- An older ICP roadmap projects $25-50k/month by month 6 using FB/Insta ads. This contradicts the Master Strategy (zero paid marketing, realistic ranges) and the locked constraints. Resolution: Master Strategy wins. Targets below are €8-10k/month by month 9-12, founder-led only. The old projection is deleted from planning.

- The Investor Deck implies an active raise. The Master Strategy puts HealthSpan behind a validation gate. Resolution: Master Strategy wins. HealthSpan gets a hard 4 hours/week cap, validation actions only, no investor meetings until the gate criteria are met.

- The Content Strategy's ambition (multi-platform, podcast, newsletter, blog SEO) exceeds the bandwidth this OS allows. Resolution: content is capped at 8 hours/week total across everything. Anything that does not fit inside the cap gets batched, delegated, or parked. Consistency at lower volume beats sporadic volume.

# 1. EXECUTIVE SUMMARY

The strategy is done. The next 12 months are a sales execution problem wearing a founder's calendar.

One objective governs everything: a predictable O!Sapiens coaching business producing €8-10k/month. The engine is simple and already designed: LinkedIn conversations feed Executive Performance Diagnostics at €350, diagnostics convert into 90-day Performance Reset containers, clients generate referrals and documented outcomes. entheogen.expert runs on autopilot rails you have already built. HealthSpan lives inside a 4-hour weekly box until it earns more.

The operating philosophy in five lines:

- Sales conversations are the first work of every weekday, not the leftover.

- Production is capped, not maximized. You already own more assets than you can convert.

- Every week produces one number that matters: qualified conversations held.

- Health is infrastructure. With your autoimmune baseline, recovery is a business control.

- When in doubt, do the smaller thing that involves talking to a buyer.

The math that makes €8-10k/month: roughly 2 Reset containers signed per month plus 6-8 diagnostics delivered plus 1-2 integration clients or a workshop. Working backward: 6-8 diagnostics needs 12-16 discovery calls, which needs 40-60 real conversations, which needs about 10 quality outreach touches per weekday. That is 90 minutes a day. Everything else in this document exists to protect those 90 minutes.

Assumption to confirm in Week 1: Reset container price. This OS assumes €2,800 (range €2,500-3,500). If your actual price differs, the pipeline math scales but the system does not change.

# 2. THE ONE THING

Daily proactive sales conversations on LinkedIn and in the warm network, protected as the first 90 minutes of every working day.

Why this and nothing else:

- It is the only activity that converts your existing assets into money within 30-90 days.

- It fails only from inconsistency, and inconsistency is your documented pattern under context-switching load. So the design principle is not motivation. It is calendar architecture: the block happens before email, before content, before the app, before anything with a dopamine reward attached.

- Every other system in this document (content, offers, dashboard, health) either feeds this block or protects it.

Why everything else is secondary: content builds authority that makes conversations easier, but content without conversations is a museum. The app is optionality, not income. entheogen.expert compounds on rails. Delivery matters, but delivery without pipeline is a practice that dies with each cohort of clients.

The test of any week: did 10+ qualified conversations happen? If yes, the week worked regardless of what else did not. If no, nothing else that happened matters.

# 3. 90-DAY EXECUTION PLAN (July - September 2026)

## Week 1: Clean the runway

Objectives: remove friction from selling. No new assets.

Projects and deliverables:

- Rewrite LinkedIn profile: pure O!Sapiens positioning, remove entheogen references, headline focused on outcome ("I help founders and executives rebuild energy, sleep and decision clarity in 90 days"), featured section pinned to Diagnostic booking.

- Confirm and write down final pricing: Diagnostic €350, Reset container (decide the number, put it in writing, do not touch it for 6 months).

- Build the prospect list: 100 names. Warm network first (former FANATIC contacts, corporate colleagues, workshop attendees, podcast guests, Liz-style practitioner allies), then 2nd-degree ICP matches.

- Set up minimal CRM: one spreadsheet or Notion board. Columns: name, source, stage (contacted / replied / conversation / discovery / diagnostic / proposal / client / referral source), last touch, next action, date.

- Send the first 25 outreach messages. Yes, in week 1. The runway is cleaned by using it.

Daily behaviors: 90-minute sales block each morning. 20 minutes of commenting on ICP posts. Weekly KPIs: 25 touches sent, 5+ replies, 2+ conversations booked, profile shipped. Failure point: perfecting the profile for five days. Recovery: profile gets one 3-hour block, then ships at 85%.

## Week 2: Establish the rhythm

Objectives: the daily system runs without drama.

- 10 outreach touches per weekday (mix: new touches, follow-ups, warm reactivations).

- First 2-3 discovery calls held. Use the two-call architecture you already run: call 1 diagnoses fit, call 2 presents the diagnostic or container.

- Post 3 LinkedIn posts (from existing material, Recognition Loop structure). Zero new frameworks.

- Send 5 direct workshop pitches to warm corporate contacts (offer: 60-90 min "Performance Without Collapse" session, €1,500-3,000 depending on company size).

KPIs: 50 touches, 10 conversations, 3 discovery calls, 1 diagnostic booked. Failure point: treating replies as pen-pal chats that never convert to calls. Recovery: every reply gets a soft call offer by message 3: "Happy to share what I see. Easier to show you in 20 minutes than type it. Want me to send a link?"

## Weeks 3-4: First revenue proof

Objectives: diagnostics delivered, first container proposed.

- Deliver 2-4 diagnostics. Follow the promise exactly: 90 minutes, written protocol within 48 hours.

- Every diagnostic ends with a bridge: "You now have the map. The Reset is where we walk it together. Want me to show you what that looks like?"

- Instrument outcomes from client #1: consented intake metrics (sleep quality, energy 1-10, stress markers, one performance KPI they choose). This is the future HealthSpan dataset. It starts now or it never starts.

- Ask every diagnostic client, converted or not, for one referral: "Who else in your circle is running on borrowed energy?"

KPIs by end of month 1: 200 touches cumulative, 40 conversations, 8 discovery calls, 4 diagnostics delivered, 1 Reset signed or in proposal. Revenue target month 1: €1,500-2,500. Failure point: discovery calls happening but diagnostics not closing. Recovery: this is a script problem, not a market problem. Record calls (with consent), review where energy drops, fix one thing per week.

## Month 2: Volume and second offer

Objectives: pipeline becomes boringly consistent. Workshops enter the mix.

- Maintain 10 touches/day. Raise conversation quality by narrowing ICP based on month 1 data (who replied, who booked, who paid).

- Deliver first paid corporate workshop or lock one for month 3.

- 2 Reset containers active. Delivery: 4 sessions/month each, protocol updates, async support batched to two windows per day.

- LinkedIn cadence stable at 3 posts/week. One post per week is a client-outcome story (anonymized, with consent).

- entheogen.expert: TikTok posting runs (contractor edits from your buffer), Russian funnel emails go out on schedule, Saturday groups continue. Total founder time: under 4 hours/week.

- HealthSpan validation inside the 4-hour box: draft the deposit offer page (€49-99 refundable, founding member framing). Do not publish yet. Do not touch the deck.

KPIs month 2: 40+ conversations, 12+ discovery calls, 6 diagnostics, 1-2 Resets signed. Revenue: €4,000-6,000. Failure point: delivery eating the sales block as clients arrive. Recovery: sales block is 9:00-10:30 and immovable. Client sessions start at 11:00 earliest.

## Month 3: Consolidate and decide

Objectives: €6-8k month, first delegation, HealthSpan gate opens.

- Hire part-time editor/VA (€300-600/month) if revenue crossed €4k in month 2. Hand over: video editing, clip cutting, scheduling, CRM hygiene, transcript repurposing.

- Publish the HealthSpan deposit page to your warm audience only (email list, LinkedIn 1st degree, Telegram). Target: first 20 deposits or 20 explicit "not interested" data points. Both are wins. Both are information.

- Referral system formalized: every completing or mid-point client gets the referral ask with a concrete incentive (a free follow-up session for a successful referral).

- Run the Quarter 1 review against the dashboard in section 9.

KPIs month 3: 3 active Resets, 6-8 diagnostics, 1 workshop delivered. Revenue: €6,000-8,000. Success criteria for the quarter overall: €12-16k cumulative revenue, 25+ diagnostics-or-discovery-calls delivered, outcome tracking live on every client, TikTok and Russian funnel running at under 4 founder-hours/week, zero brand bleed incidents. Failure points for the quarter: (1) conversation volume collapsed in any 2-week stretch, (2) a new project appeared, (3) the app consumed more than its box. Recovery for all three: same move. Return to the One Thing, cancel the intruder, tell me and I will help you kill it cleanly.

# 4. THE IDEAL WEEK

Built around your energy pattern (deep work mornings), Bechterev's-appropriate daily movement, and the Saturday group commitment. Times are Barcelona.

Monday - Thursday (the engine days)

- 07:00-08:00. Wake, light exposure, mobility routine (non-negotiable for AS: spine mobility, 20-30 min), breakfast.

- 08:00-08:45. Movement or walk. No phone. This is where your best thinking happens anyway.

- 08:45-09:00. Plan the day: pick the 3 outcomes, review CRM next-actions.

- 09:00-10:30. SALES BLOCK. Outreach, follow-ups, discovery calls when possible. Phone on do-not-disturb for everything else. This block is the business.

- 10:30-11:00. LinkedIn engagement: comment on 5-8 ICP posts, reply to your post comments.

- 11:00-13:00. Client delivery (sessions, protocols, diagnostic write-ups).

- 13:00-14:00. Lunch away from screens. Real rest, not scroll-rest. You teach this.

- 14:00-16:00. Second delivery block, or on Tue: content batching (write 3 posts for the week in one sitting), or on Thu: HealthSpan box (4h/week lives here, Thu 14:00-16:00 plus overflow Fri).

- 16:00-16:30. Admin, async client messages (window 1 of 2).

- 16:30-17:30. Buffer / overflow / learning (sales craft study 2x per week: call recordings, one chapter, one skill).

- 17:30-18:00. Shutdown ritual: update CRM, log the day's numbers (touches, conversations, calls), write tomorrow's top 3, close laptop.

- Evening: life. Second async window 20 min max around 20:00 if needed, then off.

Friday (systems day)

- Morning: sales block as usual (09:00-10:30). Pipeline does not take Fridays off.

- 11:00-12:30. Weekly review (template in section 16) + dashboard update.

- 12:30-14:00. Lunch, long walk.

- 14:00-16:00. Batch block: record TikTok batch every second Friday (8-10 videos in one session from your script library), otherwise podcast/Russian funnel maintenance.

- 16:00-17:00. Next week planning, calendar architecture, close.

Saturday

- Morning: personal, training.

- Integration group (time-boxed: 30 min prep max, session, 15 min notes).

- Rest of day off.

Sunday

- Fully off. No CRM, no LinkedIn, no "quick checks." Your nervous system is the product demo. An inflamed, depleted founder selling stress regulation is a contradiction clients can smell.

Total working hours: roughly 40-44. Sales and pipeline: ~10-12. Delivery: ~12-15. Content: ~6-8 (capped). HealthSpan: 4 (capped). Admin/review/learning: ~6.

# 5. THE DAILY OPERATING SYSTEM

Morning: light, mobility, movement, then plan. The first cognitive act of the workday is outreach, not input. No email, no feeds, no podcasts about business before the sales block. Input before output is how high-agency people procrastinate.

Midday: real lunch break. One body scan: jaw, shoulders, breath. You wrote the course on this.

Afternoon: delivery and batched creation. Async messages in two windows only (16:00, optional 20:00). You are not a chat service, and Reset clients respect boundaries that are stated on day one.

Evening: hard stop by 18:00 four days a week. Overwork for you is not a badge, it is inflammation.

Shutdown ritual (10 min, daily): log three numbers (touches, conversations, calls booked), update CRM next-actions, write tomorrow's top 3, note energy score 1-10. Fifteen seconds of honesty beats an hour of Sunday guilt.

Weekly review (Friday, 45-60 min): section 16 template. Numbers first, feelings second, decisions third.

Monthly review (last Friday, 2h): full dashboard, offer mix, pricing check (up or hold, never panic-down), one experiment maximum approved for next month, kill-list refresh.

Quarterly review (half day, offsite from your desk): strategy-vs-actuals against the Master Strategy, HealthSpan gate check, delegation decisions, pricing revision window.

Annual review: re-run the Master Strategy document against reality. Book it now: last week of June 2027.

# 6. THE SALES OPERATING SYSTEM

## Targets

- Daily (weekdays): 10 outreach touches. Mix: 4 new first-touches, 4 follow-ups, 2 warm reactivations. Plus 5-8 strategic comments on ICP posts.

- Weekly: 50 touches, 10+ real conversations (a human replied with substance), 3+ discovery calls held, 1-2 diagnostics booked.

- Monthly: 200 touches, 40 conversations, 12-16 discovery calls, 6-8 diagnostics, 1-2 Reset containers signed.

## Conversion assumptions (v1, replace with actuals after 60 days)

- Touch to reply: 20-30% (warm-weighted list; cold ICP will run 10-15%).

- Reply to real conversation: 50%.

- Conversation to discovery call: 25-30%.

- Discovery to diagnostic: 50%.

- Diagnostic to Reset: 30-40%.

- Chain check: 200 touches → ~45 conversations → ~13 calls → ~6-7 diagnostics → ~2 Resets. The math closes. If any link underperforms by more than a third for two consecutive weeks, fix that link only. Do not redesign the funnel.

## DM cadence (per prospect)

- Touch 1: personalized opener referencing something real (their post, role change, shared context). No pitch.

- Touch 2 (3-4 days later if no reply): one useful observation or resource relevant to their situation. Still no pitch.

- Touch 3 (5-7 days later): direct and honest: "I work with founders on exactly this. If energy, sleep or decision fatigue is a live topic for you, happy to show you what I see in a short call. If not, no problem at all."

- After touch 3: move to nurture (they see your content), revisit in 60 days. Never chase past three. Executives respect restraint.

## Comment cadence

5-8 comments per weekday on posts by ICP members and adjacent voices. Comments add a mechanism or a reframe, never "Great post!" One comment per day should be mildly contrarian. That is where your profile visits come from.

## Discovery call (Call 1, 20-30 min)

Structure: their situation (10 min, mostly listening) → mirror and name the pattern (5 min, this is where you win, your calibration skill is the differentiator) → honest fit verdict (yes / no / refer out) → if yes, offer the Diagnostic as the logical next step, price stated plainly, no discount.

## Diagnostic (the product that sells the product)

Deliver exactly as promised: 90 minutes, written protocol in 48 hours. The protocol document is your best salesperson: specific, personalized, minimum-effective-dose. End every diagnostic with the bridge question. Track: diagnostic-to-Reset rate is the single most important conversion number in the business.

## Closing process (Reset)

Proposal is one page: their situation in their words, the 90-day arc, what is included, price, start date, one guarantee element (e.g., first two weeks: if the fit is wrong, full refund, no friction). Send within 24 hours of the bridge conversation. Follow up once at 72 hours, once at day 7, then release.

## Referral process

Three moments: mid-container win, completion, and 30 days post. Script: "Results like yours usually exist in clusters. Who in your circle is performing well externally but running on borrowed energy? An intro to one person is the biggest compliment you can pay this work." Referral incentive: one follow-up session gifted.

## CRM workflow

One board, seven stages, updated daily in the shutdown ritual. Rule: no prospect exists outside the CRM, and every prospect has a next-action with a date. A prospect without a next action is a decision you have not made.

## Pipeline metrics (weekly, three numbers only)

- Conversations held.

- Diagnostics booked.

- Proposals outstanding. Everything else is monthly.

# 7. THE CONTENT OPERATING SYSTEM

Hard cap: 8 founder-hours per week across all content, all brands. Content serves the pipeline. When content competes with the pipeline, content loses.

## LinkedIn (O!Sapiens, primary)

- 3 posts/week: Tue, Wed or Thu, morning. Written in one Tuesday batch (60-90 min total).

- Rotation: (1) mechanism post (Recognition Loop: mirror → normalize → mechanism → practical step), (2) client-outcome story (anonymized, consented), (3) contrarian/myth-bust ("this is data, not opinion" voice).

- No external links in body. Soft CTAs. One post per month mentions the Diagnostic directly. That is enough; the DMs do the selling.

- Newsletter: not now. Parked until €8k/month is stable for two consecutive months. Your list nurture already exists in the Russian funnel; duplicating the machine in English before cashflow is complexity before proof.

## TikTok (entheogen.expert, maintenance mode)

- The 100-script buffer is the asset. Batch-record 8-10 videos every second Friday (2h). Contractor edits (or you, capped at 1h/week until the hire). Posting runs 1/day at 14:00 on schedule.

- Cover frames carry the hook. No new script development this quarter. The library is deep enough.

- Scale decision (2/day) only at ~500 followers, per existing rule.

## Telegram / Russian funnel

- Existing email sequence runs. One personal, trust-building Telegram post per week (15 min, honest, educator voice, zero selling).

- The Russian paid cohort is a month 4-6 decision, triggered by funnel signals (replies, quiz completions), not by calendar enthusiasm.

## Podcast

- Decision: finish the Leonie re-record and publish. Then move the podcast to opportunistic cadence (record only when a guest or topic serves positioning, max 1/month). Weekly podcast production fails the decision filter on cashflow speed and energy. Authority per hour is much higher in LinkedIn posts and diagnostics right now.

## Blog / SEO

- Russian SEO advantage is real but slow. One article per month, repurposed from existing podcast transcripts by the VA/contractor once hired, with your 30-min edit pass. Zero from-scratch writing this quarter.

## Repurposing chain (the leverage rule)

Everything flows downhill from what already exists: podcast transcript → blog article → 3 LinkedIn posts → 2 Telegram posts → TikTok scripts already exist. You create once per week (Tuesday batch + every-other-Friday recording). Everything else is transformation, and transformation is delegable.

# 8. THE OFFER EXECUTION SYSTEM

Priority 1: Executive Performance Diagnostic (€350)

- Revenue potential: €2-3k/month standalone, plus it is the gateway to everything.

- Time: 90 min session + 90 min protocol write-up (AI-assisted, template-driven, target: cut write-up to 60 min by month 2).

- Sales trigger: discovery call verdict "yes." Ideal client: founder/exec with named symptom (sleep, energy crashes, decision fatigue).

- Upsell path: Reset (30-40% target). Cross-sell: corporate workshop when the client has a team.

- Automation: intake form pre-call, protocol template, booking link, payment link. All buildable in one afternoon.

Priority 2: Performance Reset (90-day container, ~€2,800, confirm price Week 1)

- Revenue potential: the core. 3 concurrent = €8.4k/quarter recurring rhythm.

- Time: 4 sessions/month + protocol updates + async (batched). ~5 h/month per client.

- Capacity ceiling: 6 concurrent clients before delivery eats the sales block. At 5 concurrent, raise the price.

- Sales trigger: diagnostic bridge. Upsell: alumni quarterly check-in retainer (€200-300/month, design in month 4). Cross-sell: workshop, or (privately, if signals emerge and only client-initiated) integration work under the other brand, handled with full separation discipline.

Priority 3: Corporate workshop "Performance Without Collapse" (€1,500-3,000)

- Revenue potential: €3-9k/quarter at 2-3 workshops. Feeds 1:1 pipeline (every room contains 1-2 future diagnostics).

- Time: 4h prep first time, 1h thereafter (same deck, calibrated). Sales trigger: warm corporate network pitch + every Reset client with a team.

Priority 4: entheogen.expert integration coaching (€120-180/session, 3-month container option)

- Revenue potential: €1-2.5k/month at maintenance effort. Sales trigger: TikTok/Telegram/website inbound + Saturday group soft pathway + Awaken listing.

- Rule: inbound only this quarter. No proactive selling effort. The flywheel does the work; your hours do not.

Priority 5: Courses (SapiensOS 101/Core/Deep, Habits on Udemy)

- Role: lead magnets and credibility assets, not revenue lines. Zero development hours. Mention Habits course in diagnostic follow-ups and workshop closings as free continuation.

Priority 6: SapiensOS Reboot group program

- Parked until 10+ diagnostic-alumni exist to invite. Group offers built before an audience of buyers exists are how coaches burn a month for four signups.

HealthSpan: not an offer yet. It is a validation project with a deposit page. It enters this list only after 50+ deposits.

# 9. THE BUSINESS DASHBOARD

One page. Filled in Friday review (weekly row) and last Friday (monthly). If a metric does not change a decision, it is not on the dashboard.

Weekly (leading indicators):

- Outreach touches sent (target 50)

- Conversations held (target 10)

- Discovery calls (target 3)

- Diagnostics booked (target 1-2)

- Proposals outstanding (count)

- LinkedIn posts shipped (3) and profile views (trend only)

- Energy average, 1-10 (from daily log)

- Sleep quality average (you track this anyway; it belongs on the business dashboard because it predicts your close rate two weeks out)

Monthly (lagging indicators):

- Revenue by offer (Diagnostic / Reset / workshop / integration / other)

- New Reset clients signed; active Reset count

- Diagnostic-to-Reset conversion %

- Reply rate and conversation rate (funnel health)

- Referrals asked / received

- Content hours actually spent vs. 8h cap

- HealthSpan box: hours spent vs. 4h cap, deposits count

- Cash position and months of runway

Quarterly:

- Revenue vs. plan (Q3 2026: €12-16k; Q4: €18-24k; Q1 2027: €24-30k)

- Client outcomes documented (count in dataset)

- Founder dependency check: what % of revenue required your live hours

- Pricing decision (up / hold)

- HealthSpan gate status

- One thing killed this quarter (if the answer is nothing, the review failed)

Health metrics (weekly, three only): mobility sessions completed (target 6-7), average bedtime consistency, inflammation/pain flag (green/amber/red, subjective). Red for two consecutive weeks triggers automatic workload reduction: sales block stays, everything else shrinks 30%.

# 10. THE DECISION FILTER

Before saying yes to anything new:

- Cashflow within 90 days? 2. Strengthens one brand without bleed? 3. Uses your rare strengths (translation, calibration, trust)? 4. Needs money you do not have? 5. Adds operational complexity? 6. Feeds or drains energy? 7. In scope ethically? 8. Can AI or a contractor carry 60%+ of it? Fails 4+: no. Passes but requires >4h/week: it must replace something, name the something first.

Before launching anything: Do 10 real humans demonstrably want it (replies, deposits, bookings, not likes)? Is there an existing asset that delivers 80% of it? What is the kill criterion and date, written down before launch?

Before creating content: Does this serve an ICP pain cluster I already mapped? Can it be made from existing material? Is it inside the 8h cap? Would I rather spend this hour on two conversations, and if honest-yes, do the conversations.

Before building anything (tools, funnels, pages, decks): Has selling it manually hit a ceiling? Manual first, always. A founder who builds before selling is decorating a shop with no customers.

The 72-hour rule: any idea arriving with excitement waits 72 hours before receiving a single hour. Generators respond to real signals. Excitement is not a signal; a buyer is.

# 11. THE KILL LIST AS BEHAVIORAL RULES

Where you will self-sabotage, predicted in advance, with the prevention wired in:

- The New Framework Trap. Week 5 or 6, pipeline feels grindy, and a brilliant new model/course/funnel idea appears. It will feel like strategy. It is avoidance. Rule: no new frameworks, courses, or funnels until €8k/month has happened twice. Write ideas in a "Q1 2027 parking lot" note and close the note.

- The Polish Spiral. A protocol, post, or page gets a third revision pass. Rule: two passes maximum on anything client-facing except legal/medical-adjacent claims. Ship at 85%. Your 85% is the market's 95%.

- The App Gravity Well. An investor replies, a competitor launches, an article about longevity funding appears, and suddenly HealthSpan feels urgent. Rule: 4h/week box, Thursday afternoons. Anything app-related outside the box goes into a note for Thursday. No exceptions, including exciting ones. Especially exciting ones.

- The Free Generosity Leak. A diagnostic-grade conversation happens for free in DMs, or a group attendee gets a private mini-session. Rule: generosity budget is defined: Saturday groups, free content, Udemy course. Everything beyond that has a price. "I go deep on exactly this in the Diagnostic" is a complete sentence.

- The Podcast Relapse. Guest invitations are flattering and feel like authority. Rule: 1 recording/month max, and only if the guest is an ICP-adjacent door-opener (investor, clinic lead, corporate buyer).

- The Third-Language Platform Fantasy. Spanish content, Instagram revival, YouTube strategy. Rule: new channels are a 2027 conversation, triggered by an existing channel converting, never by boredom.

- The Brand Bleed Slip. One clever crossover post connecting performance and psychedelics for LinkedIn. Rule: never. If the idea is genuinely good, it goes on the entheogen.expert site as an article, unlinked to LinkedIn.

- The Intensity Crash. Three great weeks, then a 60-hour week, then a flare-up and a dead fortnight. Net progress: negative. Rule: weekly hours capped at 45. The health protocol (section 13) is enforcement, not suggestion.

# 12. THE DELEGATION ROADMAP

- Now (€0 threshold, AI): call prep briefs, outreach personalization drafts, protocol templating, post drafts from transcripts, CRM formulas. Already your strength; keep AI in preparation roles, you in relationship roles.

- At €4k/month (first hire): part-time editor/VA, €300-600/month, 10-15h/week. Scope: TikTok editing, scheduling, transcript-to-blog repurposing, CRM data entry, podcast post-production. SOP: one Loom video per task, filmed once while you do it, stored in a shared folder. Hire from your practitioner/community network first; brand sensitivity matters more than raw skill.

- At €8k/month sustained (month 2 consecutive): upgrade VA hours or add a second contractor for design/landing pages; consider a booking/billing tool subscription stack (still under €100/month total).

- At €12k/month: associate facilitator for Saturday groups (trained, revenue-shared), freeing the weekend fully. Begin documenting the Reset delivery method for a future associate coach (this is also SapiensOS certification groundwork, but that product remains parked).

- Never delegated: discovery calls, diagnostics, Reset sessions, pricing decisions, brand voice final pass.

# 13. THE HEALTH PROTOCOL

Framed as what it is: infrastructure maintenance for the business's only asset, with an autoimmune constraint that makes this non-optional.

- Sleep: fixed wake time 7 days/week, bedtime consistency over duration heroics, screens off 60 min before bed. Sleep is on the business dashboard because it is a leading indicator of your close rate and your inflammation.

- Movement: daily spine mobility (20-30 min, morning, non-negotiable with Bechterev's), 3x/week strength or swim, daily walking built into the schedule (the 08:00 block). Prolonged sitting is a disease accelerator for you specifically: 50-minute work blocks, stand and move 5.

- Nutrition: your gluten-free anti-inflammatory system is already dialed. The rule is simpler: protect it under stress. Stress-eating shortcuts are the first crack; batch-prep on Sundays removes the decision.

- Workload limits: 45 h/week hard cap. Max 3 client sessions/day. Max 2 discovery calls/day. No calls after 17:00 except one designated evening slot/week for other time zones.

- Travel rules: no more than one work trip/month this year; every trip costs a recovery day, budget it in the calendar before booking.

- Warning indicators (amber): morning stiffness lasting longer than usual, sleep fragmenting, irritability in client sessions, skipping mobility twice in a week, "I'll just finish this" past 19:00 twice in a week.

- Amber response (automatic, pre-decided): next-day schedule loses everything except sales block and booked client sessions; one full recovery day within 72 hours; reassess Friday.

- Red (flare or two amber weeks): delivery pauses where possible, sales block shrinks to follow-ups only, medical support if needed, zero guilt. A two-week planned deceleration beats a two-month forced one. You have lived this math before.

# 14. THE FINANCIAL ROADMAP

Monthly revenue targets (blended, all offers):

- Jul 2026: €1.5-2.5k | Aug: €3-4k | Sep: €5-7k

- Q4 2026: €6-8k/month average (Resets compounding, workshops entering)

- Q1 2027: €8-10k/month (the objective, achieved through 3-4 concurrent Resets + 6-8 diagnostics + 1 workshop/month + integration inbound)

- Q2 2027: hold €8-10k, decide: scale coaching toward €12-15k (raise prices, add group Reboot from alumni pool) or shift surplus attention to HealthSpan if the gate opened.

Offer mix at target (illustrative €9k month): Resets €5.6k (2 new signings/month at €2.8k) + Diagnostics €2.1k (6) + workshop €1.5k + integration €0.8k. Adjust to your confirmed pricing.

Pipeline requirement to sustain it: the section 6 weekly numbers. They do not relax after success; they are the success.

Cash rules: 6 months personal runway is the first savings goal before any discretionary spend; business costs stay under €500/month until €8k months (VA + tools); no personal money into HealthSpan beyond a pre-committed €1k validation budget (landing page, deposit processing).

Hiring thresholds: as per section 12. Investment priorities in order: runway → VA → sales skill development (a course or coach for YOU on closing, budget €500-1,500, likely the highest-ROI euro you will spend this year) → tools → everything else.

# 15. FIRST 30 DAYS (day-level plan)

The daily invariant (every weekday, always): 09:00-10:30 sales block (10 touches + follow-ups + calls), 10:30-11:00 comments, shutdown ritual with numbers logged. Days below list only what is UNIQUE on top of the invariant.

Week 1

- Day 1 (Mon): Confirm Reset price in writing. Build CRM board. Start prospect list (goal 40 names today, warm first). Success: price locked, 40 names, 5 touches sent (yes, day one).

- Day 2 (Tue): Prospect list to 100. LinkedIn profile rewrite, single 3-hour block, ship it. Success: profile live, entheogen references gone.

- Day 3 (Wed): Set up booking link + payment link + diagnostic intake form (one afternoon, done crudely). Success: someone could pay you today without friction.

- Day 4 (Thu): Full 10-touch block. Draft workshop one-pager from existing SapiensOS material (90 min, two passes). Success: pitch-ready PDF.

- Day 5 (Fri): First weekly review. Batch-write next week's 3 LinkedIn posts. Success: 25 touches on the week, 5+ replies, review done, posts queued.

- Weekend: Sat group as usual. Sun off.

Week 2

- Day 8 (Mon): Send workshop pitch to 5 warm corporate contacts. Success: 5 sent, personalized.

- Day 9 (Tue): Post 1 live. First discovery calls this week: hold whatever is booked; if zero booked, every reply thread gets the soft call offer today.

- Day 10 (Wed): Post 2. Reactivate 10 dormant warm contacts (former clients, FANATIC network, podcast guests) with the honest reconnection message.

- Day 11 (Thu): Post 3. HealthSpan box (first one): draft deposit page copy only, 2h, close the box.

- Day 12 (Fri): Review. KPI check: 100 touches cumulative? 15+ conversations? 2+ calls held? If any is <60%, the recovery action is written into next week before you close the laptop.

Weeks 3-4 (rhythm + first money)

- Day 15 (Mon): Deliver diagnostic #1 if booked (protocol within 48h, template it as you write it).

- Day 16 (Tue): Batch posts. Client outcome instrumentation live: intake metrics form finalized.

- Day 17 (Wed): Protocol #1 delivered. Bridge conversation held.

- Day 18 (Thu): HealthSpan box: deposit page built (not published). Referral ask made to any completed diagnostic.

- Day 19 (Fri): Review. Record first TikTok batch (8-10 videos, 2h) from script library.

- Day 22-25: Diagnostics #2-3 delivered. First Reset proposal sent within 24h of any bridge-yes. One workshop follow-up round.

- Day 26 (Fri): Review week 4.

- Day 29-30: Month 1 review against targets: 200 touches, 40 conversations, 8 calls, 4 diagnostics, 1 Reset signed or proposed, €1.5-2.5k revenue. Write the three sentences: what worked, what broke, what one thing changes in month 2.

Success criterion for the whole 30 days, above all numbers: the sales block happened at least 20 of 22 weekdays. If it did, the business now exists as a behavior, and the revenue is arithmetic from here.

# 16. ACCOUNTABILITY SYSTEM

Daily checklist (5 boxes, on paper or one Notion line): ☐ Mobility done ☐ Sales block done (10 touches) ☐ Numbers logged ☐ CRM next-actions current ☐ Shutdown by 18:00

Weekly review template (Friday, 45 min):

- The three numbers: conversations / diagnostics booked / proposals out.

- Revenue collected this week.

- Hours: sales / delivery / content / app / admin (rough).

- Energy average and health flag (green/amber/red).

- One thing that worked (do more). One thing that broke (fix or kill). One thing I avoided (name it honestly; the avoided thing is usually the important one).

- Next week's top 3, in the calendar before closing.

Monthly CEO scorecard (0-10 each): pipeline discipline, revenue vs. target, delivery quality (client feedback), brand separation held, caps respected (content 8h, app 4h), health protocol adherence, one-thing focus. Below 6 on any two: that pair is the entire agenda of the next monthly review.

Execution score (weekly): sales blocks completed / 5. This is the score. Everything correlates with it.

Momentum score (weekly, subjective 1-10): "Is the machine getting easier to run?" Three consecutive declines while execution score stays high means something structural is wrong (offer, ICP, or script). Bring it to me and we debug the link, not the system.

External accountability: send me (or a trusted peer) the three weekly numbers every Friday. Not the narrative. The numbers. Narratives are where slippage hides; numbers are where it surrenders.

## CLOSING NOTE

This OS is deliberately smaller than your capability. That is the point. You do not have a talent, knowledge, or asset problem. You have a concentration problem, and concentration is enforced by structure, not by intention.

The system matters more than the insight. Integration starts on Monday. So does the sales block.